## Sheet1
Risk ID | Risk Description | Affected System | Control Gap | Likelihood | Impact | Inherent Risk | Existing Controls | Residual Risk | Risk Owner | Treatment Plan | Status | Due Date
R-001 | Terminated users may retain access to business applications | Jira, GitHub | Offboarding validation is incomplete | Medium | High | High | HR offboarding checklist | Medium | IT Operations | Implement weekly HR-to-access reconciliation and require access removal evidence | Open | 2026-10-30
R-002 | Privileged access may be granted without documented approval | Jira, GitHub, Microsoft 365 | Privileged access approval evidence is incomplete | Medium | High | High | Manager approval process | Medium | IT Security | Require documented approval for all privileged accounts and review admin access quarterly | Open | 2026-10-30
R-003 | User access reviews may not provide complete audit evidence | Jira, Confluence, GitHub | Access review sign-off evidence is incomplete | Medium | Medium | Medium | Quarterly access review process | Low | IT Operations | Centralize access review sign-offs and require manager approval evidence for all reviewed users | Open | 2026-11-15
R-004 | MFA exceptions may increase unauthorized access risk | Microsoft 365 | MFA exception documentation is incomplete | Medium | High | High | Conditional access policy | Medium | IT Security | Document all MFA exceptions and review excluded users monthly | In Progress | 2026-10-15
R-005 | Audit logs may not be retained long enough for investigations | Jira, GitHub, Microsoft 365 | Log retention requirements are unclear | Medium | Medium | Medium | Audit logging enabled | Low | Security Operations | Document log retention requirements and review logging coverage quarterly | Open | 2026-11-15
R-006 | Critical and high vulnerabilities may exceed remediation timelines | Application Infrastructure | Vulnerability SLA tracking is inconsistent | High | High | Critical | Vulnerability scanning process | High | Security Operations | Implement SLA-based vulnerability tracking with owners, due dates, and remediation status | Open | 2026-10-15
R-007 | Production changes may be implemented without complete approval evidence | Production Systems | Change approval documentation is incomplete | Medium | Medium | Medium | Change ticketing process | Low | Engineering | Require approval evidence before production promotion | Open | 2026-11-01
R-008 | Backup recovery may not be fully validated | Critical Systems | Restore test evidence is incomplete | Medium | High | High | Backup policy and scheduled backups | Medium | IT Operations | Document restore testing results and retain quarterly evidence | Open | 2026-11-15
R-009 | Vendor contracts may not clearly define breach notification requirements | Third-Party Vendor | Vendor security review checklist is incomplete | Low | Medium | Medium | Vendor questionnaire process | Low | Procurement / Security | Update vendor checklist to include breach notification and data handling requirements | Open | 2026-11-30